## Sheet1
Risks | Response Strategy | Objectives | Baseline |  |  | Analysis and response: 06/12/2020
Operational Risks |  |  | Likelihood | Impact | Risk Level
The use combination of different programmes and packages may pose a problem when deploying the application | Ensure that packages and programmes are installed correctly and tested | To have an application with 4 services deployed | Likely | High | 60% | Problems were encountered with permissions while initiating a Docker swarm via ansible
Errors in code may lead to bugs and an incomplete application | Test application is working on localhost regularly | To have an application with 4 services communicating with each other | Very Unlikely | Very High | 40% | All necessary features have been covered
Deactivation of GCP virtual machine | Clone repository in a new VM and reinstall packages | Host the application on a GCP virtual machine | Very Unlikely | Medium | 20% | All packages are stored in a requirements.txt file and Git repository is updated frequently
Security Risks |  |  | Likelihood | Impact | Risk Level
Man in the middle attack | Ensure keys are kept private and not exposed | Ensure application is protected against MITM attacks | Very Unlikely | Very High | 30% | Secret keys are stored in known folders and not published on public repositories
DDoS Attack | Attack detection, upstream filtering and allowing/denying specific IP addresses | Ensure that the application is protected against DDoS attacks | Very Unlikely | Very High | 30%
Objectives Risks |  |  | Likelihood | Impact | Risk Level
Application does not have 100% testing coverage | Ensure regular testing and coverage testing | Ensure 100% testing coverage | Fairly likely | Medium | 40% | Application code was tested with 100% coverage early on in the project